## Introduction
Purpose of the Opportunity Tracker
As part of establishing a robust data and AI strategy, I have created an 'Opportunity Tracker' to help businesses consistently identify, evaluate and prioritise data and AI initiatives. This could be low hanging fruit and more business case initiatives / projects. In complex environments where ideas often outpace capacity, this framework brings structure, discipline and alignment to the innovation pipeline. It ensures the organisation invests in the right things: initiatives that deliver tangible benefits, are technically viable and contribute to strategic goals. The 'Opportunity Tracker' uses a consistent scoring framework to assess each initiative across two key dimensions: Benefit Realisation and Technical Feasibility. This dual lens helps decision-makers balance ambition with execution capability, identifying high-value, low-effort opportunities that can deliver immediate impact, while also flagging transformative projects that may require phased investment or further validation. By quantifying these dimensions, the tool drives objectivity, removes bias, and creates a shared language across business and technology teams. The PICK analysis than helps visualise it for wider business teams. Importantly, this framework enables the business to manage its portfolio of data and AI investments with greater transparency and agility. It supports better planning, smarter resource allocation, and clearer trade-off decisions in alignment with enterprise priorities. Over time, it helps embed a culture of data-driven decision-makingm where ideas are not just approved because they sound promising but because they demonstrably drive value and are feasible to deliver.

## Opportunity Tracker
ID | Opportunity Name | Description | Business Functions | Business Pillar | Value Score (/15) | Volume OR Market Opportunity (1 - 5) | Operational Efficiency Impact OR Customer Impact (1 - 5) | Strategic Alignment (1 - 5) | Benefit Realistion Comments | Complexity Score | Technical Complexity (1 - 5) | Risk Appetite (1 - 5) | Technical Feasibility Comment
1 | Customer Segmentation Engine | Use clustering algorithms to group B2B and B2C customers based on behaviours and value to improve targeting and personalisation. | Marketing | Increase Sales Revenue, Increase Customer Satisfaction | 13 | 5 | 4 | 4 | Improves marketing ROI and personalisation, leading to higher engagement and conversion. | 7 | 3 | 4 | Requires clean customer data and integration with CRM and campaign tools.
2 | Sales Forecasting with ML | Predict future sales using historical data, seasonality, and pipeline insights to improve planning accuracy. | Sales and Business Development | Increase Sales Revenue, Reduce Operational Costs | 12 | 4 | 3 | 5 | Enables better inventory, staffing, and financial planning. | 5 | 2 | 3 | Moderate complexity. Historical sales and pipeline data must be structured and clean.
3 | Churn Risk Prediction | Use classification models to identify customers likely to churn and enable proactive retention efforts. | Product | Increase Customer Satisfaction, Increase Sales Revenue | 14 | 4 | 5 | 5 | Helps retain high-value customers through timely interventions and improved service. | 6 | 3 | 3 | Feasible if churn labels and interaction history are available and well maintained.
4 | AI-Based Support Ticket Routing | Use NLP to automatically classify and route support tickets based on urgency and issue type. | Operations | Increase Customer Satisfaction, Reduce Operational Costs | 11 | 3 | 4 | 4 | Reduces handling time and ensures quicker, more accurate customer service responses. | 7 | 4 | 3 | Requires sufficient labelled support ticket data and integration with service platform.
5 | Automated Expense Categorisation | Leverage ML to auto-classify employee expenses to reduce manual workload and improve accuracy. | Finance | Reduce Operational Costs, Increase Employee Engagement | 10 | 3 | 3 | 4 | Improves finance team efficiency and enhances employee experience with faster reimbursement. | 6 | 2 | 4 | Straightforward implementation with access to past expense records and categories.
6 |  |  |  |  | 0 |  |  |  |  | 0
7 |  |  |  |  | 0 |  |  |  |  | 0
8 |  |  |  |  | 0 |  |  |  |  | 0
9 |  |  |  |  | 0 |  |  |  |  | 0
10 |  |  |  |  | 0 |  |  |  |  | 0
11 |  |  |  |  | 0 |  |  |  |  | 0
12 |  |  |  |  | 0 |  |  |  |  | 0
13 |  |  |  |  | 0 |  |  |  |  | 0
14 |  |  |  |  | 0 |  |  |  |  | 0
15 |  |  |  |  | 0 |  |  |  |  | 0
16 |  |  |  |  | 0 |  |  |  |  | 0
17 |  |  |  |  | 0 |  |  |  |  | 0
18 |  |  |  |  | 0 |  |  |  |  | 0
19 |  |  |  |  | 0 |  |  |  |  | 0
20 |  |  |  |  | 0 |  |  |  |  | 0
21 |  |  |  |  | 0 |  |  |  |  | 0
22 |  |  |  |  | 0 |  |  |  |  | 0
23 |  |  |  |  | 0 |  |  |  |  | 0

## Eval Framework & Scoring Matrix
Benefit Realisation |  |  |  | Technical Feasibility
The Benefit Realisation section evaluates how well a data or AI initiative contributes to tangible business outcomes. It focuses on factors such as market opportunity, customer value, efficiency gains, and alignment to strategic goals. This ensures that initiatives are not just technically interesting but are grounded in solving real problems, unlocking growth, or enabling transformation. By scoring opportunities on their potential to create measurable value, organisations can prioritise work that delivers meaningful impact to customers, revenue, operations, or strategic advantage. |  |  |  | The Technical Feasibility section assesses the effort, complexity, and risks involved in implementing a proposed solution. It considers aspects such as delivery effort, integration complexity, stakeholder readiness, and risk tolerance. This ensures initiatives are realistically scoped and resourced, preventing investment in projects that are overly ambitious or fragile in execution. By evaluating feasibility alongside benefit, organisations can make informed decisions that balance aspiration with practicality, leading to more successful and sustainable outcomes.
Category | Description | Score | Definition | Technical Complexity | Assesses the overall effort, complexity, and resource demand involved in deploying the solution. | 1 | Minimal effort required; out-of-the-box solution, fast to deploy, minimal resourcing needed.
Volume | Assesses how often the task occurs and how broadly it affects the organisation. | 1 | Infrequent activity with limited operational impact. |  |  | 2 | Low effort; minor setup or tailoring needed, largely pre-built and low in complexity.
|  | 2 | Happens occasionally and influences a few functional areas. |  |  | 3 | Moderate effort; mix of existing and customised components, manageable delivery effort.
|  | 3 | Recurs periodically, with moderate operational reach. |  |  | 4 | Considerable effort; largely custom with multiple inputs, moderate-to-high complexity and workload.
|  | 4 | Regularly executed and affects multiple parts of the business. |  |  | 5 | Very complex and resource-heavy; fully bespoke solution requiring extensive time, skills, and support.
|  | 5 | High-frequency activity that is vital across several core business units. | Risk Appetite | Gauges the level of risk involved in implementing and sustaining the initiative. | 1 | Very low risk; proven approach with minimal uncertainty or stakeholder resistance.
Operational Efficiency Benefit | Measures the potential for improving process time, cost or resource allocation. | 1 | Minor or negligible efficiency gains. |  |  | 2 | Low risk; generally stable with minor foreseeable issues.
|  | 2 | Slight improvements limited to specific teams or processes. |  |  | 3 | Moderate risk; known implementation or adoption risks that are manageable with planning.
|  | 3 | Moderate gains that benefit several functions or workflows. |  |  | 4 | High risk; notable unknowns, potential resistance or operational impact if not carefully handled.
|  | 4 | Notable improvements that deliver clear savings in effort, cost, or throughput. |  |  | 5 | Significant risk; high uncertainty, resistance from key stakeholders, or serious business exposure.
|  | 5 | High-impact improvements that transform how resources are used or time is spent.
Strategic Alignment | Evaluates how closely the activity supports overarching strategic goals and priorities. | 1 | Little or no relevance to business strategy or transformation efforts.
|  | 2 | Partial connection, but not a significant contributor to business direction.
|  | 3 | Generally aligned and supports operational or departmental goals.
|  | 4 | Directly contributes to strategic priorities and medium-term initiatives.
|  | 5 | Strongly aligned with long-term business strategy and critical transformation objectives.
Deliver new customer facing solutions/opportunities
Market Opportunity | Evaluates the size, clarity, and ease of entry into the potential market. | 1 | Very limited or niche market with minimal demand or scalability.
|  | 2 | Small market size, though some interest or emerging trends may exist.
|  | 3 | Moderate market with steady or rising interest.
|  | 4 | Substantial market with evident and growing demand.
|  | 5 | Large, well-established market with high and sustained demand potential.
Customer Benefit | Measures how well the opportunity addresses customer needs or pain points. | 1 | Low relevance to customers; unclear or limited benefit.
|  | 2 | Offers minor improvements or conveniences to the customer experience.
|  | 3 | Adds meaningful value; clearly solves a recognised customer issue.
|  | 4 | Delivers strong value or addresses a major pain point.
|  | 5 | Highly differentiated or breakthrough solution with significant customer impact.
Strategic Alignment | Gauges how closely the opportunity supports business goals and leverages existing capabilities. | 1 | Not aligned with strategic direction or internal strengths.
|  | 2 | Weak fit; may require new skills, technology, or a shift in focus.
|  | 3 | Generally aligned, though some investment or adaptation may be necessary.
|  | 4 | Closely aligned and builds on current capabilities and strategic direction.
|  | 5 | Fully integrated with business strategy and leverages existing strengths and priorities.

## PICK Chart Template
PICK Model – Data & AI Initiative Prioritisation
| Low Effort / Easy to Implement | High Effort / Complex to Implement
High Business Value | ✅ Implement Quick wins worth pursuing immediately. Low complexity, high return. | 🔍 Challenge Strategic initiatives with big impact but require more resources, planning or capability uplift.
Low Business Value | 🤔 Pursue Selectively Low-cost initiatives that may support incremental improvements or learning. | ❌ Kill or Park Expensive initiatives with little proven benefit. Not worth further investment.